## Sheet2 (hidden)
Contact Name
Category Name
Maximum transaction value
Transaction message
transaction image
profile image

## QE DashBoard
API Issues | API Issues | Tokobook QE Status
New | 0
Reopen | 0
Fixed | 0
Closed | 2
Not an Issue | 0
Suggestion | 0
Deferred | 1
Mobile Issues | Mobile Issues
New | 0
Reopen | 0
Fixed | 0
Closed | 0
Not an Issue | 0
Suggestion | 0
Deferred | 0
API Testing | API Testing Status
Pass | 18
Fail | 0
No Run | 3
Blocked | 0
Mobile Testing | Mobile Testing Status
Pass | 0
Fail | 0
No Run | 0
Blocked | 0
API Testing | API Automation Status
Yes | 0
No | 32
Mobile Testing | Mobile Automation Status
Yes | 0
No | 0

## Test Plan
Area | Category | Summary | Comments | Estimation | Status
Test Case Design and Planning
Test planning and test case design |  |  |  |  | On Track
Functional Testing | API Testing | Account Management |  |  | On Track
Transactions
Friends
Reminders
Reports
Sharing
| Installation & launch | Installation
Re-installation
Uninstall
Splash pages
| Mobile Functional Testing | Account Management
Transactions
Friends
Reminders
Reports
Sharing
Bottom Navigation
Menubar
Filter / Search / Sort
Menu bar
| Integration Testing | API Layer /Authentication
|  | 3rd party integrations | Email / whatsapp/SMS
| Interruption testing | Incoming calls
Camera activated
Alarm clocks
Low battery notifications
Enabling data transfer mode
Navigations in between Apps
| Permission | Contacts
Gallery /Camera
| Error Messages and Validations | Invalid Login
|  | Empty list | Transactions, Reminders, Entry, Friends
Invalid transaction amount
No Entry Message in detail view
Network unavailability issue
Backend unavailability issue
Text field description
| Globalization Testing | English
Basha
Data Compatibility
Contact Name
Maximum transaction value
Transaction message
Image Size
| Data Type | Image | png, jpg??
|  | Text Fields | English/ Basha
Compatibility testing
iOS
|  | Android | Samsung / Oppo/ Xiaomi
OS Version
Non Functional Testing | Performance Testing
Security Testing
Release Testing | Regression and Clean build Testing
App Store Testing
API Automation
Mobile Automation

## Features
Feature |  | API Feature | Mobile Feature | Comment
Account Management | Register | Create User | Register via OTP (email +mobile)
| Sign In | Login | Sign In
| Profile | Get Profile | View Profile | Creation profile is supported by create user and book. Profile is a combination of a user and a book.
|  | Update Profile | Update Profile
| Books | Get ALL BOOKS / Get Book | Select a book from the hamburger menu | Updating a book is unsupported as per now.
|  | Create Book | New book creation
|  | Delete Book | Delete existing book
Transactions |  | Get Transactions | View Transactions for all users | Retrieve All transactions - Report Retrieve active transactions - Home
Search transactions
Sort , Filter Transactions
View entries per user
View Detail Entry
|  | Add Transaction | Add an entry
|  | Update Transaction | Update an entry
|  | Delete Transaction | Delete an entry
Friends |  | Get Customers | View Friends | Auto sync is required to add , update, delete friends from phonebook
|  | Add Customer | Add new friend via app
Import friends from phonebook
|  | Update Customer | Edit new friend via app
Import Updated friend details from phonebook
|  | Delete Customer | Delete friend via app
Delete friends who are not in phonebook
Reminders |  | Get Reminder | View Reminders
Send a push notification to the borrowers to remind
|  | Update Reminder Settings | Update Reminders
Reports |  | Get Report | View Report : All transactions
Search Report
Sort, Filter report
|  | Get Download Report Content | Download Report
Share the transaction file through email
Sharing |  | N/A | Sharing the App download link with friends / Refer a friend
Bottom Navigation |  | N/A | Navigation
Menu Bar |  | N/A | Menu Items

## API Testing
# | Test Cases | Automatable | Automated | Test Data | Expected Results | Testing Status Latest Cycle | Defect ID | Testing Status Previous Cycle | Defect ID
Account Management
Create User /api/v1/users
1 | Verify API as a contract | Yes | No |  | Required: { fullName: [string] email: [string] password: [string] mobileNo: [string] } Optional: { language: [String] } | Pass |  | Pass
2 | Verify correct HTTP status code | Yes | No |  | POST/ 200 | Pass |  | Pass
3 | Verify response payload | Yes | No |  | { "status": "SUCCESS", "message": "Successfully created user", "data": { "userId": "uid-dbf40c2b-2d80-4c9d-9ca2-3ad72c91edbc" } } | Pass |  | Pass
4 | Verify response headers | Yes | No |  | "Accept: application/json" "Content-Type: application/json" | Pass |  | Pass
5 | Verify with valid full Name | Yes | No | John , Johe Doe |  | Pass |  | Pass
6 | Valid email | Yes | No | test@abc.com , test@abc.com.io |  | Pass |  | Pass
7 | Invalid email | Yes | No | test , test@abc, test.com | 400 | Pass |  | Pass
8 | Verify Password correct format | Yes | No |  | Password must contain at least: 1 Uppercase 1 Lowercase 1 Number 6 characters | Pass |  | Fail | API- Def2
9 | Invalid Password format | Yes | No | test12, TEST12, 123456, TestUser, Test User | 400 | Pass |  | Pass
10 | Valid mobile Number | Yes | No | "+6281254567891" |  | Pass |  | Pass
11 | Invalid mobile number | Yes | No | 628125456 without plus sign | 400 | Pass |  | Pass
12 | Verify whether email and mobile are unique | Yes | No |  |  | No Run |  | No Run
13 | Empty Fields (fullName, email, password, mobileNo) | Yes | No |  | 400 | Pass |  | Pass
14 | Verify Optional fields - Language | Yes | No |  |  | Pass |  | Pass
15 | Verify Invalid Language | Yes | No |  | 400 | Pass |  | Pass
16 | Verify multiple invalid fields | Yes | No |  |  | Pass |  | Pass
17 | Verify ability to send the data in Basha | Yes | No |  |  | Pass |  | Pass
18 | Verify Spellings Response body , Request Body , Error messages | Yes | No |  |  | Pass |  | Pass
19 | Verify Incorrect endpoint | Yes | No | http://192.168.1.18:8080/tokobook/api//users | 404 | Pass |  | Pass
20 | Verify internal server error | Yes | No |  | 500 | No Run |  | No Run
21 | Authentication | Yes | No |  | 403 | No Run |  | No Run
Login /api/v1/users/login
26 | Verify API as a contract | Yes | No |  | Required: { email/ mobileNo = [string], password = [string] }
27 | Verify correct HTTP status code | Yes | No |  | POST/ 200
28 | Verify response payload | Yes | No |  | { "status": 200, "message": "Success", "data": { "userId": "uid-9642c64e-1288-4e08-8303-17c1914ed49" } }
29 | Verify response headers | Yes | No |  | "Accept: application/json" "Content-Type: application/json"
30 | Correct username - email | Yes | No | test@abc.com , test@abc.com.io
31 | Correct username - mobile | Yes | No |  | Mobile Number can use +62, or usually use 0 to replace +62 Digits: at least 9 digits exclude +62 or 0 at the beginning Normally the mobile number is 12 digits For example: +6281234567890 = 081234567890
32 | Verify Password correct format | Yes | No |  | Password must contain at least: 1 Uppercase 1 Lowercase 1 Number 6 characters
33 | Invalid Password format | Yes | No | test12, TEST12, 123456, TestUser, Test User
34 | Empty Fields (username, password) | Yes | No
35 | Verify ability to send the data in Basha | Yes | No
36 | Verify Spellings Response body , Request Body , Error messages | Yes | No
Get Profile
Update Profile
Get ALL BOOKS / Get Book
Create Book
Delete Book
Transactions
Get Transactions
Add Transaction
Update Transaction
Delete Transaction
Friends
Get Customers
Add Customer
Update Customer
Delete Customer
Reminders
Get Reminders
Add Reminder Settings
Reports
Get Report
Get Download Report Content

## Mobile Testing
# | Test Cases | Automatable | Automated | Test Data | Expected Results | Testing Status | Defect ID | Testing Status | Defect ID
Account Management
Register via OTP (email +mobile)
Sign In
View Profile
Update Profile
Select a book from the hamburger menu
New book creation
Delete existing book
Transactions
View Transactions for all users
Search transactions
Sort , Filter Transactions
View entries per user
View Detail Entry
Add an entry
Update an entry
Delete an entry
Friends
View Friends
Add new friend via app
Import friends from phonebook
Edit new friend via app
Import Updated friend details from phonebook
Delete friend via app
Delete friends who are not in phonebook
Reminders
View Reminders
Send a push notification to the borrowers to remind
Update Reminders
Reports
View Report : All transactions
Search Report
Sort, Filter report
Download Report
Share the transaction file through email
Sharing
Bottom Navigation
Menu Bar

## API Issues
# | Issue | Screenshot/ Test Data | Status | Severity | Priority | Resolution | Reported Date | Closed Date
1 | Better to implement seperate error messages for validations | - | Closed | Low | Low |  | 2019-11-29
2 | Cannot use passwords without special charachters | e.g. : Am12345 | Closed | Minor | Medium |  | 2019-11-29
3 | Error when entering a string with back slash Error: JSON parse error: Unrecognized character escape '3' (code 51); nested exception is com.fasterxml.jackson.databind.JsonMappingException: Unrecognized character escape '3' (code 51) at [Source: (PushbackInputStream); line: 2, column: 13] (through reference chain: com.tokoin.tokobook.dto.request.UserRequestDto["fullName"])", "path": "/tokobook/api/v1/users | e.g. : Am/12345 | Deferred | Minor | Low | Need to verify with frontend test | 2019-12-03

## Mobile Issues
# | Issue | Platform | Type | Screenshot | Status | Severity | Priority | Reported Date | Closed Date

## Blockers
# | Date | Blocker | Mitigation Plan | Closed Date
1 | 2019-11-19 | Verification with end user similar devices | Get support from PO for UAT verification | 2019-11-20
2 | 2019-11-29 | Verification with a Indenosian service provider to verify the OTP | Get support from PO for verification

## Notes
# | Notes
1 | If language field name is incorrect, by default language will set to English